DAMASCUS TRANSIT SYSTEM

نقل دمشق

Upgrade Plan

Make it easier to run, easier to add buses, and harder to break

Version 1.0  ·  June 2026

Contents

# 1. Executive summary

DTS works today — buses show on the map and the pipeline is live. But running it currently means looking after a five-box, do-it-yourself chain: custom firmware on a 2G modem, an MQTT broker, a relay, and a webhook. Every box is one more thing to flash, watch, and fix. This plan makes the system markedly easier in four moves you can take in order — each one is useful on its own, so value lands early.

The single biggest lever Switch from DIY hardware to off-the-shelf 4G GPS trackers that Traccar already understands. Because you already built the /api/traccar/position webhook, this one change lets you delete three of the five boxes — the custom firmware, the MQTT broker, and the relay. Adding a bus becomes: buy a tracker, type its ID into the admin, assign a route and driver.

Nothing here throws away what you have. The phone-based driver tracking and the existing HTTP path stay as fallbacks, and you can pilot the new hardware on a single bus before committing the fleet.

# 2. Where the friction is today

| Area | How it works now | Why it’s harder than it should be |
| --- | --- | --- |
| Adding a bus | Per-bus firmware file, flash the board, hand-edit IDs | Doesn’t scale; every bus is a small engineering task. |
| Hardware | ESP32 + SIM900 (2G) DIY build | 2G is being switched off; DIY means you own every bug. |
| Moving parts | Broker + relay + webhook, all bespoke | Five things in series — any one breaking stops the map. |
| Knowing it broke | You notice the map is empty, then read logs | No alert; failures are found by luck, not by the system. |
| Daily admin | Vehicle, route, driver, device, approval = 5 screens | Setup is fiddly and easy to get half-done. |

# 3. The big idea: fewer boxes

## Today

DIY firmware → SIM900 (2G) → MQTT broker → relay → /api/traccar/position → Supabase → map

## Target (recommended)

4G GT06 tracker → Traccar (VPS) → /api/traccar/position → Supabase → map Three boxes gone. One Traccar service replaces the firmware, the broker, and the relay — and Traccar decodes the trackers for you.

Traccar is the open-source tracking server that natively speaks the GT06 protocol these cheap trackers use. It receives each device and forwards the position to the webhook you already have — so the rest of DTS (database, SSE, maps, hover cards) is unchanged.

# 4. Phased roadmap

Four phases, sequenced so the safety net comes first and the big hardware change is piloted before rollout.

| Phase | Goal | Rough effort |
| --- | --- | --- |
| 0 — Quick wins | Fix known issues; add a safety net | Hours |
| 1 — Easy onboarding | Adding a bus = type an ID, no flashing | 1–2 weeks |
| 2 — Hands-off reliability | The system tells you when a bus goes silent | ~1 week |
| 3 — Simpler daily ops | One wizard, one dashboard | 1–2 weeks |
| 4 — Modernize | Retire 2G; fewer services to run | Ongoing |

PHASE 0 · QUICK WINS · this week

- Fix the duplicate device id. The demo vehicle “تكسي 1” still carries gps_device_id = DTS002, the same id as your real tracker, so live fixes can attach to the wrong bus. Clear it.

- Add a dead-man’s-switch monitor. Have the relay ping a free heartbeat service every cycle; if fixes stop arriving, you get an email/Telegram within minutes instead of discovering an empty map later.

- Make the VPS self-heal. Set restart: unless-stopped on the broker and relay containers so a crash or reboot recovers on its own.

- Rotate the test secrets. Change the broker password and webhook secret away from the temporary values used during setup.

PHASE 1 · EASY BUS ONBOARDING · 1–2 weeks

Target experience: to add a bus you buy a tracker, type its ID into the admin, and assign a route and driver. No files, no flashing. Two ways to get there:

### Path A — off-the-shelf 4G tracker (recommended)

Buy a hardwired 4G GT06 tracker (about $12–18 each; cheaper in bulk). They include engine cut-off, ignition (ACC) detection and over-speed alarms, and run on 9–36 V straight from the bus. Run a Traccar server on your existing VPS; it decodes the tracker and forwards positions to /api/traccar/position. Register the device id to a vehicle from the admin. No firmware for you to maintain, ever.

### Path B — keep DIY, but one universal firmware

If you specifically want in-house hardware: flash one identical firmware to every board. On boot it reads its own chip id and self-registers through a pairing endpoint; you then “claim” the device to a bus in the admin. Keeps your ESP32 stack and removes the per-bus file, but you still own the firmware and the modem.

|  | Path A — 4G GT06 + Traccar | Path B — universal DIY firmware |
| --- | --- | --- |
| Firmware to maintain | None | One (shared) — still yours to support |
| Add-a-bus time | Minutes (type the IMEI) | Minutes (claim the device) |
| Unit cost | ~$12–18 (bulk ~$10) | ~$27 (LilyGO 4G board) + assembly |
| Ruggedness | Sealed, vehicle-grade | Depends on your enclosure |
| Moving parts removed | Firmware + broker + relay | Per-bus files only |
| Best for | The real fleet | Tinkering / full control |

PHASE 2 · HANDS-OFF RELIABILITY · ~1 week

- “Silent bus” alerts. You already record last_position_update per vehicle, and /api/health/deep already returns 503 when the whole feed is stale. Extend that to per-vehicle: if an approved, in-service bus goes quiet for N minutes, raise an alert through the alerts pipeline you already have.

- External uptime monitor. Point a free monitor at /api/health/deep (Healthchecks.io heartbeats, or self-host Uptime Kuma on the VPS) so an outage emails/pings you from outside the system.

- Status page. A simple shared page showing live buses, last-fix age, and service health — useful for the ministry too.

PHASE 3 · SIMPLER DAILY OPS · 1–2 weeks

- One “Add a bus” wizard that creates the vehicle, route, driver, device pairing and approval in a single screen — instead of five separate pages.

- One-click approve straight from the dashboard.

- Dashboard tiles: buses live now, buses silent, trips today, approvals pending — the numbers you actually check.

- Bulk import (CSV) for vehicles, routes and drivers, to stand up a fleet quickly.

PHASE 4 · MODERNIZE & CUT MOVING PARTS · ongoing

- Retire 2G. Across the Middle East, 2G is being switched off between 2025 and 2030, and LTE Cat-1 is the new default for trackers. Standardize on 4G (Path A trackers, or a LilyGO 4G board if you stay DIY).

- Collapse broker + relay. With Path A, the MQTT broker and the custom relay both disappear — you maintain one Traccar service instead of two bespoke containers.

- Lean on managed pieces where it helps (your database is already managed via Supabase); keep Traccar self-hosted on the VPS you already pay for.

# 5. Effort vs. impact

| Move | Effort | Impact on “easier” |
| --- | --- | --- |
| Phase 0 quick wins | Very low | High |
| Path A trackers + Traccar | Medium | Very high |
| Silent-bus alerts + monitor | Low–medium | High |
| Add-a-bus wizard + dashboard | Medium | Medium–high |
| Universal DIY firmware (Path B) | Medium–high | Medium |

# 6. What it costs

- Trackers: ≈ $12–18 each for 4G GT06 units (bulk toward $10); a DIY LilyGO 4G board is ≈ $27 plus assembly.

- Monitoring: free tier (Healthchecks.io ~20 checks; Uptime Kuma self-hosted is free).

- Traccar: open-source and free; runs on the VPS you already have.

- Net: mostly your time. The only per-bus cost is the tracker, which you’d buy either way.

# 7. Risks & sequencing

- Do Phase 0 first so a safety net exists before you change anything.

- Pilot Path A on one bus alongside the current setup; only switch the fleet once a single tracker → Traccar → map round-trip is proven.

- Keep the phone/HTTP path as a fallback throughout the migration.

- Check coverage first. Confirm the tracker’s 4G bands with the local carrier before any bulk order.

- Ship through your normal flow. Code changes go out via the existing push-and-PR workflow, so each phase deploys the same safe way you use now.

# 8. Recommended next step

Start with Phase 0 now I can (1) clear the duplicate DTS002 device id so live data always lands on the right bus, and (2) wire a heartbeat monitor so you’re alerted the moment the feed stops. In parallel, the highest-leverage Phase 1 step is to stand up a Traccar test instance on the VPS and trial one off-the-shelf 4G tracker.

# Sources

Hardware, network and monitoring references used for this plan:

- Traccar-verified GPS hardware (4G wired, GT06/808)

- GT06 4G tracker — product & pricing example (SkyWonder GPS)

- 2G/3G sunset for IoT — migration guidance (Telenor IoT)

- The global 3G sunset and IoT connectivity (Teltonika)

- LilyGO T-A7670G ESP32 4G + GPS board (overview)

- Best free uptime / heartbeat monitoring tools, 2026