DamascusTransit

Revival Analysis & Multi-Week Roadmap

Prepared 24 May 2026   ·   For: 3dtitans   ·   Base branch: main (Apr 27 snapshot)

1. Executive Summary

The project is in much better shape than the typical “stopped and abandoned” codebase. As of the last recorded run on 18 April 2026 the test suite was 307/307 green, all four CI workflows were passing, the Vercel deployment was healthy, and the production database had 8 routes, 54 stops, 24 vehicles, and 18 active drivers. The pause is roughly five weeks long, not five years. Restart cost is small if you reuse what is already there.

Your stated direction is to convert the mobile clients to Flutter. Before committing to that path it is important to recognise that the repository already contains a fully scaffolded Capacitor 6 mobile wrapper: Android and iOS projects, a 464-line bridge layer (geolocation, background tracking, FCM/APNs push, biometric auth, camera), a Play Store listing draft in Arabic and English, and a documented release pipeline. A Flutter rewrite throws this work away and rebuilds it in Dart.

Bottom line: If the only goal is a real Android/iOS app, the fastest path is to finish what is in mobile/ — you can be on the Play Store in weeks, not months. Choose Flutter only if you have a separate, concrete reason: smoother native map performance for drivers, a long-term mobile-first roadmap, or a team that already writes Dart. The rest of this document is structured so you can make that call deliberately rather than by default.

2. State of the Project Today

Vital signs at last run (Apr 18, 2026)

| Test suite | 307 / 307 passing across 12 test files (~14m 39s runtime) |
| --- | --- |
| CI workflows | 4/4 green: lint, test+coverage, gtfs-validate, security-scan, db backup |
| Production /api/health | HTTP 200 — DB + Redis connected |
| Production /api/stats | HTTP 200 — 18 of 24 vehicles active, 8 routes, 54 stops |
| Open security findings | 9 (2 HIGH, 4 MEDIUM, 3 LOW). 5 fixed since prior scan. 0 known CVEs in dependencies. |
| Dependency freshness | All clean per pip-audit. 9/11 packages have non-blocking updates available. |
| Last commit window | ~5 weeks of stagnation since 18 Apr 2026 |

What’s in the codebase

| Area | What’s there | LOC / count |
| --- | --- | --- |
| Backend API (FastAPI) | 20 routers, 7 core modules, 26 documented endpoints, Pydantic schemas, JWT+RBAC, PostGIS spatial helpers, SSE stream, Traccar webhook (HMAC), GTFS-RT, push notifications, Redis rate limiting | 6,224 LOC Python |
| Database | schema.sql (15 tables, RLS), 6 migrations applied, seed.sql, GTFS export folder | 541 + 323 LOC SQL + 6 .sql migrations |
| Web apps (PWA) | Dashboard (511), Analytics (691), Admin (2607), Passenger (1042), Driver (1272) | ~6,100 LOC HTML/JS |
| Shared frontend lib | capacitor-bridge.js, error-handler.js, i18n.js | ~700 LOC JS |
| Mobile (Capacitor 6) | Android + iOS native projects, capacitor.config.ts, BUILD.md guide, Play Store listing draft (AR/EN) | Scaffolded, not yet shipped |
| Tests | 12 Python test modules + Playwright JS specs | 7,178 LOC tests |
| DevOps | Dockerfile + Dockerfile.prod, docker-compose (dev/prod), Vercel config, nginx config, ministry-deploy.sh, simulate_gps.py, backup/restore scripts | — |
| Docs | README, DEPLOY, DR, DOCKER_MINISTRY_DEPLOY, GTFS_SUBMISSION, CONTRIBUTING, DEMO_ACCOUNTS, business + financial plans, weekly reviews | 12 markdown + 12 docx reports |

main vs feat-dashboard-deploy

feat-dashboard-deploy is the older snapshot (8 April). main (27 April) already contains all of its non-trivial dashboard work and goes further: it adds capacitor-bridge.js, the mobile folder with Capacitor wrapper, Playwright tests, the client_log router, an extra business plan, more daily reports, and an updated schema. There is nothing on the feature branch that is not already in main. Recommendation: treat main as the sole base of truth and archive the feature branch.

3. Known Liabilities to Resolve Before Going Further

These items were already known and tracked when work paused; they should be cleared before any rewrite begins, because they affect any future client (web, Capacitor, or Flutter).

| ID | Issue | Severity | Effort |
| --- | --- | --- | --- |
| H1 | Rate-limit bypass via X-Forwarded-For spoofing in api/core/cache.py | HIGH | ~2 hrs |
| H2 | Rate limiter fails open when Redis unavailable | HIGH | ~2 hrs |
| M1 | No JWT revocation on password change | MEDIUM | ~3 hrs |
| M3 | Operator ID not validated against current user | MEDIUM | ~2 hrs |
| M4 | Optional auth hides authorisation gaps on some endpoints | MEDIUM | ~3 hrs |
| — | PR #15 (vehicle tracking SPA) stale since 31 March — merge or close | Hygiene | ~1 hr |
| — | feature/websocket-tracking-upgrade has 9 unmerged commits behind a closed PR — delete | Hygiene | 30 min |
| — | Dependency refresh: fastapi 0.115→0.136, pydantic 2.10→2.13, sentry-sdk, upstash-redis, pywebpush (minor); bcrypt 4→5 and gtfs-realtime-bindings 1→2 are major upgrades that need test runs | Hygiene | ~1 day |

4. The Mobile Question — What To Build the Apps With

You want native Android and iOS apps. There are three credible paths from the current state of the repo. The trade-offs are mostly about how much existing code you preserve and how much you rewrite, not about whether the apps work.

Path A — Finish the Capacitor 6 wrap (already started)

Reuse the existing passenger/ and driver/ PWAs as a WebView, with native plugins behind the bridge.

Path A — Pros & Cons

| PROS | CONS |
| --- | --- |
| About 70% of the work is already in the repo (capacitor.config.ts, native projects, 464-line bridge, Play Store listing). | WebView UX is recognisably web on iOS (especially scroll-bounce and form chrome). |
| Zero rewrite — passenger (1,042 LOC) and driver (1,272 LOC) HTML/JS keep working as-is. | Real-time map performance on low-end Android devices is bounded by MapLibre GL JS, not native. |
| Background GPS, push (FCM/APNs), camera, biometric auth are already wired in the bridge layer. | Background tasks on iOS are awkward — Apple actively constrains JS background work; the @capawesome-team plugin papers over this but it is not as robust as a native iOS app. |
| One codebase serves web, Android, and iOS. Bug fixes ship everywhere at once. | App Store review can be tougher for thin web-wrappers (Apple guideline 4.2). Mitigated here because the bridge adds real native capabilities (GPS, push, biometrics), but worth knowing. |
| Realistically deployable to the Play Store in 4–6 weeks of part-time work. | Long-term, you still maintain HTML/JS rather than typed mobile code. |
| Cheapest path if the web apps already do what you need them to do. |  |

Path B — Rewrite passenger + driver in Flutter (your proposal)

Keep the FastAPI backend, the Supabase database, and the web dashboard + admin panel. Replace only the two mobile-facing PWAs with a Flutter codebase that builds to Android, iOS, and optionally web.

Path B — Pros & Cons

| PROS | CONS |
| --- | --- |
| True native rendering on both platforms — buttery 60–120 fps map panning even on low-end devices. | You discard ~2,300 LOC of working HTML/JS (passenger + driver) and the entire mobile/ folder. The Capacitor work is sunk cost. |
| Single Dart codebase produces Android, iOS, and (with Flutter web) a high-fidelity web build if you ever want it. | Realistic rebuild: 8–14 weeks of focused part-time work for both apps to reach feature parity, longer if you also localise + RTL all over again. |
| Best-in-class offline support via Hive / Drift / sqflite — much stronger than service-worker caching for the passenger PWA today. | Two languages and two build systems in the project (Python + Dart, plus the existing JS for web admin/dashboard). Onboarding gets harder. |
| Background location on both platforms is mature in Flutter (flutter_background_geolocation, geolocator). More reliable than the Capacitor plugin on iOS over long shifts. | You still need a web dashboard and admin panel — Flutter web is not the right tool for those, so the JS frontend stays. |
| Strong static typing (Dart null safety) prevents an entire class of bugs you currently have to test for in JS. | App Store / Play Store submission still applies. Distribution friction from Syria (Google Play developer account billing, Apple Developer Program payment) is a real hurdle independent of framework choice. |
| Excellent ecosystem for maps (flutter_map for MapLibre/OSM, mapbox_gl, google_maps_flutter) and for transit primitives. | Map performance is rarely the bottleneck for transit apps at city scale — MapLibre GL JS handles 500+ markers fine. The native-rendering advantage may not show up in your real workload. |
| Future-friendly: if you later want a watch companion app or a kiosk display, Flutter targets are wider than Capacitor. | JWT auth, RBAC, SSE stream client, GTFS parsing, Traccar event handling — all needs reimplementing in Dart. |

Path C — Stay on PWA only (no native shell)

Drop the Capacitor work and ship the passenger/driver apps as installable PWAs only.

Path C — Pros & Cons

| PROS | CONS |
| --- | --- |
| Zero new work — the apps already work as PWAs today. | Drivers really want a real app icon, push notifications, and reliable background GPS. PWAs on iOS are weak on all three. |
| No App Store / Play Store dependency. Updates ship the moment Vercel deploys. | iOS Safari still does not support periodic background sync; driver GPS will stop when the app is backgrounded. |
| Avoids App Store distribution issues entirely (relevant given Syria-related payment restrictions). | Passengers expect to find the app in the Play Store. Discovery suffers without a listing. |
|  | You give up biometric login on driver phones (Web Authentication API exists but is fiddly on Android WebView). |

Side-by-side decision matrix

| Criterion | A: Capacitor (finish) | B: Flutter (rewrite) | C: PWA only |
| --- | --- | --- | --- |
| Time to first Play Store build | 2–4 weeks | 10–16 weeks | N/A |
| Native iOS background GPS reliability | Medium | High | Low |
| Map render performance on low-end devices | Medium | High | Medium |
| Existing code preserved | ~95% | ~40% (backend + admin only) | ~100% |
| Hiring / maintainability long-term | JS / TS | Dart (smaller pool) | JS / TS |
| Cost of an additional native API (e.g. NFC ticket) | 1 plugin | 1 plugin | Not possible |
| Codebase complexity | Web + thin native | Web + Dart + native | Web only |
| App Store risk (Apple 4.2) | Low-Medium | Very Low | N/A |
| Right answer when… | Web UX is acceptable and time is short | Mobile UX is the product and you have a team | You only need an internal tool |

My honest recommendation: Go with Path A (finish Capacitor) for the next 4–6 weeks to get a real Play Store presence and let drivers/passengers use the apps in the wild. If after a few weeks of real usage the WebView UX or background-GPS reliability turns out to be the bottleneck — and only then — start Path B as a deliberate, well-scoped follow-on. Treat Flutter as a v2 decision driven by data, not a v1 default. You also keep optionality: the FastAPI backend is unchanged in any scenario, so the choice is reversible and the cost of being wrong is small.

5. If You Decide to Go Flutter Anyway

These are the architectural decisions you do not want to make on the fly. Lock them down before writing the first Dart file.

| Project layout | Monorepo: keep current root unchanged, add mobile_flutter/ alongside mobile/. Do not delete mobile/ until Flutter reaches parity. |
| --- | --- |
| State management | Riverpod 2 (preferred over Bloc for solo developer; better testability than Provider; supports code-gen). |
| Networking | Dio + Retrofit for typed API clients generated from openapi.json (already 117 KB of OpenAPI 3.0 spec in the repo — use it). |
| Auth | JWT via flutter_secure_storage for refresh tokens; biometric_storage for biometric-gated token unlock; mirror the existing role-based guards. |
| Realtime | Native SSE via flutter_client_sse to consume /api/stream. Don’t reinvent — your backend already speaks SSE. |
| Maps | flutter_map (OSM/MapLibre tiles, MIT-licensed) for the passenger app; consider mapbox_maps_flutter for the driver app if you want native rendering with offline tile packs. |
| Background GPS | flutter_background_geolocation (transistorsoft) is the gold standard. Free for OSS; paid for closed. Budget for the licence. |
| Push | firebase_messaging (FCM) for Android, APNs via Firebase for iOS. You already have a /api/push router and a push-token flow in the existing bridge. |
| Offline storage | Drift (SQLite) for relational route/stop cache; Hive for KV (last-known-position, preferences). |
| Localisation | flutter_intl for AR/EN; reuse existing translation keys from i18n.js where possible. |
| Testing | flutter_test for widget tests; integration_test for end-to-end; reuse the smoke_test_production.py against the deployed API. |
| CI | GitHub Actions matrix: existing python job + new flutter analyze + flutter test + fastlane build for Android AAB. |

6. Multi-Week Revival Roadmap

Twelve weeks, three phases. Phase 1 is mandatory regardless of mobile path. The Flutter timing below assumes you choose Path B; if you stay on Capacitor it collapses to roughly half the calendar.

Phase 1 — Reanimate the platform (Weeks 1–2)

Cloud account inventory — log into Supabase, Vercel, Upstash, Sentry, Resend, Firebase. Document which accounts still exist, whose card is on file, billing status, and whether MFA is enabled.

Local environment — clone main, copy .env.example to .env, fill in credentials, run docker compose up, confirm /api/health returns DB + Redis connected.

Run the test suite — pytest. Target: 307/307 still pass against the current dep set. If anything regresses, fix or pin before doing anything else.

Branch hygiene — delete feature/websocket-tracking-upgrade, decide on PR #15 (merge or close), tag the current commit as v1.0.0-pre-revival.

Dependency refresh — bump minor versions (fastapi, pydantic, sentry-sdk, upstash-redis, python-dotenv, pywebpush). Defer bcrypt 5 and gtfs-realtime-bindings 2 to a separate branch with a full test run.

Clear the 2 HIGH security findings (H1 trusted-proxy fix, H2 rate-limiter fail-closed). These take a day combined and unblock the security backlog.

Verify production — run smoke_test_production.py against the live Vercel URL. Confirm SSE stream works.

Output of Phase 1: green CI, green tests, fresh deps, a clean main, and a current production deploy that you can confidently iterate on.

Phase 2 — API + Contract freeze (Weeks 3–4)

Treat openapi.json as the source of truth. Regenerate it from the live FastAPI app and diff against the checked-in version to catch drift.

Add the remaining MEDIUM security fixes (M1, M3, M4). After this round, every endpoint has consistent auth semantics.

Document the SSE event shape (event names, payload schema, heartbeat cadence) in markdown-files/technical/SSE_Contract.md — your mobile client will depend on this whether Flutter or Capacitor.

Stand up a staging environment on Vercel (preview deploy) with its own Supabase project, so the mobile client can be tested without touching production.

Decision gate: confirm Path A or Path B with cost/time in hand from Phase 1. Do not start Phase 3 with the question still open.

Output of Phase 2: a frozen, documented API; staging environment; firm decision on mobile path.

Phase 3a — If Path A (Capacitor)  (Weeks 5–8)

Week 5 — finish mobile/android: Firebase project + google-services.json, signing keystore, real app icons / splash, AndroidManifest permissions audit, RTL verification.

Week 6 — finish mobile/ios: APNs key in Apple Developer, GoogleService-Info.plist, real icons, Info.plist privacy strings (NSLocationAlways, NSCameraUsage, NSFaceIDUsage), test on a physical iPhone.

Week 7 — beta testing: distribute via Google Play internal testing track and TestFlight. Recruit 5 drivers and 20 passengers from the existing pilot.

Week 8 — production submission: prepare store listings (you already have a draft in mobile/PLAY_STORE_LISTING.md), submit to Play Store, submit to App Store. Set up Sentry release tagging for mobile builds.

Phase 3b — If Path B (Flutter)  (Weeks 5–12)

Week 5 — bootstrap mobile_flutter/, set up Riverpod skeleton, configure Dio with openapi.json codegen, wire CI to flutter analyze + flutter test.

Week 6 — auth flow end-to-end: login screen, JWT storage, biometric gating, role-based routing, password reset.

Week 7 — passenger app: route list, stop search (PostGIS nearest), map view with flutter_map, ETA display, offline mode with Drift.

Week 8 — passenger app continued: SSE stream consumption, vehicle marker animation, push notifications for stop proximity, AR localisation pass.

Week 9 — driver app: trip start/end flow, passenger count UI, foreground GPS, background GPS with flutter_background_geolocation, incident photo capture.

Week 10 — driver app continued: speed-violation alerts, route deviation detection client-side, biometric unlock, AR pass.

Week 11 — internal testing (TestFlight + Play internal track), bug bash, crash reporting via Firebase Crashlytics + Sentry.

Week 12 — Play Store + App Store submission, retire mobile/ folder, update README to reference the Flutter project.

Phase 4 — Sustain (ongoing)

Weekly health checks (already part of the existing operator workflow — re-enable the agent if used; otherwise add a scheduled task).

Monthly dependency audit (pip-audit, pubspec outdated, npm audit).

Quarterly security scan, re-running the existing playbook in markdown-files/technical/Security_Scan_*.md.

Public roadmap on GitHub Issues with the Now/Next/Later view to attract contributors (LICENSE is permissive — the project is already open source).

7. Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Supabase project deleted or paid-tier required after inactivity | Medium | High | Confirm Phase 1, Week 1. Export schema + data via pg_dump immediately as a backup. |
| Vercel project unlinked from GitHub | Low | Medium | Re-import in Phase 1; preview deploys will rebuild. |
| Apple Developer account billing fails from Syria | High | High | Plan distribution via a partner organisation in MENA, or use Android-only initially. Document in DEPLOY.md. |
| Google Play developer account billing fails from Syria | Medium | High | Same as above. APK side-loading is a viable interim distribution path for pilot users. |
| Flutter chosen but solo developer underestimates rewrite scope | High | High | Build a thin Flutter passenger app first (1 screen + map) in week 5 as a real estimate before committing to the full plan. |
| bcrypt 5.0 or gtfs-realtime-bindings 2.0 breaks tests after upgrade | Medium | Low | Upgrade on a feature branch; do not block the revival on these majors. |
| Sentry SDK 2.58 changes capture semantics | Low | Low | Diff release notes during Phase 1; run the integration suite. |
| PR #15 (vehicle tracking SPA) introduces merge conflict with current main | Medium | Low | Decide early (merge or close). 18-day-old PRs rot fast. |
| Real GPS hardware not available for testing | Low | Medium | scripts/simulate_gps.py already exists. Keep using it for CI. |

8. Practical Next 7 Days

If you do nothing else this week, do these in order. Each is ~1–2 hours.

Day 1 — Confirm Supabase, Vercel, Upstash, Sentry, and Firebase logins still work. Note billing status.

Day 2 — Clone main locally, run docker compose up, hit http://localhost:8000/api/health, see green.

Day 3 — pytest in the project root. Confirm 307/307 (or document what broke and why).

Day 4 — Delete the feature/websocket-tracking-upgrade branch. Decide on PR #15. Tag main as v1.0.0-pre-revival.

Day 5 — Apply the H1 + H2 security fixes. Push, watch CI go green.

Day 6 — Re-deploy to Vercel. Run scripts/smoke_test_production.py. Confirm SSE stream alive.

Day 7 — Take a deliberate decision on Path A vs Path B. Capture it as an ADR in markdown-files/technical/.

On choosing Flutter: Flutter is a legitimate choice, not a wrong one. The thrust of this document is that it is a larger and later choice than it looks from the outside, because mobile/ already exists. Whichever direction you take, the FastAPI + Supabase + PostGIS backbone is the durable asset; the mobile shell is replaceable. Decide based on whether your users’ next pain is performance (→ Flutter), presence on stores (→ finish Capacitor), or reach without installs (→ PWA).